## Gantt Chart
	Food Online Order Dynamics				0%
	Northeast Dev
	Project Manager: Mr. Foo Bar		Friday, January 19, 2018

										06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30					31
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Feb-18					Mar-18					Apr-18					May-18					Jun-18					Jul-18
			01-Feb-2018	23487	20-Feb-2108	0%	32891			01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31
	Requirements		01-Feb-2018	23487	20-Feb-2108	0%	32891	0	10
	Test current application
	Testing application	Mr. Foobar	10-Feb-2018	2	12-Feb-2018		3	0	2
	Fix Bugs	Mr. Foobar	12-Feb-2018	2	13-Feb-2018		2	0	2
	Refactoring current application
	Plan object design	Mr. Foobar	14-Feb-2018	4	19-Feb-2018		6	0	4
	Move to new object design	Mr. Foobar	18-Feb-2108	2	20-Feb-2108		3	0	2

	Milestone Phase 1 Compete		15-Feb-2018

	Test new application		16-Feb-2018	2	19-Feb-2018	0%	4	0	4
	Review unit tests	Mr. Foobar	16-Feb-2018	1	16-Feb-2018		1	0	1
	Review functional tests	Mr. Foobar	17-Feb-2018	1	17-Feb-2018		1	0	1
	Conduct all tests	Mr. Foobar	18-Feb-2018	2	19-Feb-2018		2	0	2

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		1/1/18
		3/4/18
		4/18/18
		4/20/18
		4/25/18
		5/1/18
		6/10/18
		8/15/18
		12/8/18
		12/25/18